## Slide 1
SWIPE: Streamlined Workflow to improve Physiotherapy ED Activation |  | 
Department: Nursing and Rehabilitation | Period: Aug – Dec 2025 | Facilitators/Author: Balachandran J/ See Yi Na
Sponsors (HODs): Kwan Peijun, Liang Sufang, C Uma D/o Chandra Segara | Team Leader/s: See Yi Na and Qi Hongjuan | 
Team Members: Koh Hui Ying, Derek Tan, Marni Binte Malik, Tan Pei Qi, Shahidah Bte Satu |  | 
Incredible Care QIX Award (Process Excellence)
The 6 box QIX template is brought to you by Quality Improvement Department wef 1 April 2023

## Slide 2: Sample 3
A. Define the Problem (PLAN)
Problem: Multiple phone calls by ED Staff Nurse (SN) before Physiotherapist (PT) can review patient in Emergency Department (ED).
Diagram 1: Process map for activating PT services in ED

## Slide 3: Sample 3
A. Problem Analysis (PLAN) Value Stream Map
FTQ: First Time Quality
FTQ: First Time Quality ( i.e. PT sees patient after 1 call)
PT: Processing Time
DT: Delay Time
TAT: Turn Around Time ( i.e. From time of phone call from SN to the time PT see patient)
: Delay

## Slide 4: Sample 3
A. Baseline Data
Chart: Number of Phone Calls to PT
| Pt 1 | Pt 2 | Pt 3 | Pt 4 | Pt 5 | Pt 6 | Pt 7 | Pt 8 | Pt 9 | Pt 10 | Pt 11 | Pt 12 | Pt 13 | Pt 14 | Pt 15
No of calls before PT review patient | 4 | 3 | 2 | 3 | 4 | 6 | 3 | 2 | 5 | 6 | 3 | 5 | 4 | 5 | 6
median | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
4 calls per patient required before PT assessment
No of Phone Calls
Patient
Median: 4 calls
RUN Chart

## Slide 5: Sample 3
B. Goal (PLAN) Set SMART goals | Specific, Measurable, Achievable, Relevant, Time-based |
To reduce the number of phone calls from Emergency Department staff nurses to physiotherapists from the current four calls to one call per patient within the next three months (i.e. September–December 2025) at National University Hospital (NUH).

## Slide 6: Sample 4
Communication inefficiencies
PT unable to see ED patient
SN uncertain about PT criteria
Decreased compliance to Screening Criteria
C. Problem Analysis (PLAN) Gap Analysis
You may use more than 1 problem solving tools (Gap Analysis, VSM, Paradigm, Pareto Chart)
SN does not have other avenues to contact PT if PT does not pick up call
PT might be seeing patient at time of calling, unable to pick up call
Default practice to refer to Physiotherapy
Lack of consensus between SN and PT on screening criteria
Medical Team keen to discharge patient timely
New SN unaware of criteria
Screening criteria not included in Orientation
Lack of physical reminder for criteria in work area
Lack of dedicated workstation for SN in ED
Rushed by medical team to contact PT
Medical team keen to discharge patient promptly or patient is keen for home
Early referral for PT review by medical team when patient is not medically fit
Doctors not orientated to Screening Criteria
Doctors unaware of Screening Criteria

## Slide 7
S/N | Problem | Description | People responsible | Date of implementation
1.0 | Communication inefficiencies | Team chat created for GEM nurse and PT for communication - GEM nurses to text PT after 2 unanswered call | APN Hongjuan and PT Yi Na | 25th Aug 25
2.0 | Lack of consensus between SN and PT on screening criteria | Consensus of screening criteria* between SN and PT​ * Screening criteria: Referral by Doctor/APN Agreeable for ED PT charges Carer to be available during PT session (if patient has carer) No pending medical investigation Disseminate Screening Criteria to existing ED SN | APN Hongjuan and PT Yi Na APN Hongjuan and Peiqi | 25th Aug 25 1st Sept 25
3.0 | Orientation of Screening Criteria to new SN | Include Screening Criteria into orientation program for New ED SN | APN Hongjuan and Peiqi | 1st Sept 25
D. Interventions & Action Plan (DO)

## Slide 8
Plan
Objective: To improve communication avenue between SN and PT
Hypothesis: Improve communication between SN and PT. If text message is sent, PT will acknowledge within 10 - 30mins time.
What: Create a TEAMS chat for SN and PT
Who: All ED SN and PT covering Geriatrics wards
Predicted outcomes: SN able to reach PT 100% of the time to inform PT about referral.
Plan
Do
Study
Act
Do
Teams chat created 25 August 2025
Act
Adopt and monitor
Study
Actual outcome: SN able to reach PT 80% of the time.
What went well:
During study period, there were 6 occasions where PT could not pick up phone. PT acknowledged referral for 5 occasions within 30mins.
1 referral was acknowledged more than 30mins was because PT was conducting a long caregiver training session (40mins) in ward.
D. PDSA 1.0: Communication inefficiencies
Create a Teams chat for SN and PT

## Slide 9
Plan
Objective: SN and PT have consensus on screening criteria
Hypothesis: Having a common criteria minimize calls to PT
Plan:
What: Common criteria
Who: ED SN and PT covering Geriatrics ward
Predicted outcomes: Reduce number of phone call to 1 per patient
Plan
Do
Study
Act
Do
Common Screening criteria confirmed on 25 August 2025 and disseminated to existing ED SN on 1 September 2025
Act
Adding weightbearing status into criteria
Start cycle 2.1
Study
Actual outcome: 63% of patients require 1 phone call
What went well:
Out of 24 pts, 15 patient require 1 call, 9 patients require 2 call
Reason for having 2nd call:
  Screening criteria (Did not clarify if there is carer available)
  To clarify weightbearing status
What can be improved on:
Reinforcement of screening criteria by APN Hongjuan to ED SN
After reinforcement, most 2nd phone call was due to clarification of weightbearing status for patients with fractures
D. PDSA 2.0: Lack of consensus between SN and PT on screening criteria
Common Criteria

## Slide 10
Plan
Objective: SN and PT have consensus on screening criteria
Hypothesis: Having a common criteria minimize calls to PT
Plan:
What: Common criteria + weight bearing status
Who: ED SN and PT covering Geriatrics ward
Predicted outcomes: Reduce number of phone call to 1 per patient
Plan
Do
Study
Act
Do
Inclusion of weightbearing status to screening criteria Oct 2025
Study
Actual outcome: 100% of patients require 1 phone call
What went well:
After weight bearing status was added as a criteria, all subsequent patients (53 patients) only require 1 call before PT review patient
D. PDSA 2.1: Lack of consensus between SN and PT on screening criteria
Common Criteria + weightbearing status
Act
Adopt and monitor

## Slide 11
D. PDSA 3.0: Orientation of Screening Criteria to SN
Plan
Objective: To educate new ED SN on screening criteria
Hypothesis: Orientation of Screening criteria to new ED SN to improve compliance of screening criteria before activating PT.
What: Inclusion of screening criteria to orientation of ED SN.
Who: New ED SN
Predicted outcomes: All new SN aware of screening criteria
Plan
Do
Study
Act
Do
Include Screening Criteria into Orientation of New ED SN from 1 Sept 2025
Study
Ongoing training to new ED SN
Act
Include screening criteria to new ED SN orientation

## Slide 12
Chart: Number of Phone Calls to PT
 | 1
E. Benefits / Results (CHECK)
Pre-intervention
Post-intervention
Reasons for 2nd phone call:
Did not clarify if carer available
Investigation results not out yet
Reasons for 2nd phone call:
Need to clarify lower limb weight bearing status
Need to clarify upper limb weight bearing status
No of Phone Calls
Patient
Pre Median: 4 calls
RUN Chart
Post Median: 1 calls
1 call before PT review
Turn Around time
by 67 minutes
Potential Revenue:
$247,200 a year

## Slide 13
E. Potential Revenue Missed
Turn Around Time decreased from 75 minutes to 8 minutes, a reduction by 67min.
This 67‑minute reduction allows PTs to see two additional patients, generating an estimated additional revenue of $206 per phone call.
  With an average of 5 ED calls per day that requires PT review, estimated additional revenue:
    $206 x 5= $1030 per day
    Potential revenue per month: $1030x 20= $20, 600
    Potential revenue per year: $20,600 x 12= $ 247,200
This new workflow demonstrates how improving work processes can yield substantial benefits.

## Slide 14: Sample 5
F. Strategy for Spreading/ Sustaining (ACT)
2005
2007
2008
2009
2010
2013
Training
SN and PT should orientate new staff rotating to the Emergency Department to ensure they are aware of the new workflow.
Audit Checks
Team leaders perform audits every three months (measuring compliance rates, time taken to see patients in the Emergency Department, and average number of calls made) to ensure that everyone complies with the new workflow.
Spreading
To implement this workflow in EDTU
Communication
SN and PT to communicate timely if any issues arise from this new workflow
Standard Works
To look at the peak hour of calls: re-examine manpower planning to station one PT in the Emergency Department during peak hours
What actions are required for continuous improvement? How will the results be sustained for the long run? Will the project be spread to other areas?
Systems
To translate into Epic ordering for automation – however need to ensure that SN must tick off all 4 criteria before placing a PT order

## Slide 15
F. Insights Learnt
Understanding Diverse Perspectives
Different stakeholders (clinicians, allied health, nursing staff) had varying priorities and constraints
Actively listening helps to understand concerns of different parties
Change is more sustainable when you get buy in from all the stakeholders
Communication Is Critical
Establishing additional communication avenues improve information flow and facilitate timely referral
Clear communication regarding expectations help enhanced compliance